## Feuil1
Missions | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
comprehension subjets | bar: 40
reading memory study | bar: 40 to 41
researching data | bar: 41
first views of the dataset | bar: 42
tutor meeting | bar: 43
first analyses | bar: 44 to 45
identfying NA values | bar: 44 to 45
Probelms with meto stations | bar: 46
tutor meeting | bar: 47
grouping meteos stations | bar: 48 to 49
first map | bar: 49
presenting new dataset | bar: 49
preparing December soutenance | bar: 50 to 51
validation of dataset | bar: 49
First analyses on dataset and variables | bar: 51
learning extrem data modelisation | bar: 1 to 3
first tries of modelisation | bar: 4 to 5
create a reactive map | bar: 7
train the model | bar: 6 to 7
create shiny app | bar: 8 to 13
write a notebook of the project | bar: 14 to 16
prepare the final soutenance | bar: 14 to 16